- Introduction:

UNICEF Nepal is looking for an implementing agency that have the expertise and experience working on nutrition related programme implementation particularly to scaling up maternal nutrition services with multiple micronutrient supplementation (MMS) and strengthening institutional capacity for maternal, infant and young child nutrition. The assignment under the terms of reference is as follows:

To support in capacity building activities to roll out the minimum package of maternal nutrition programme including maternal multiple micronutrient tablet (M MS) distribution in 8 districts of Madhesh Province. Under this consultancy services the implementing agency is expected to play supportive, capacity enhancing and system strengthening role across maternal nutrition and institutional development. The external technical agency will serve as technical leader, system strengthening partner and capacity building facilitator. The agency will help the government to expand and institutionalize high quality maternal nutrition services, ensure consistent commodity availability, build a competent nutrition workforce, strengthen data and supervision systems, and generate evidence to inform national policy and scale up. The role of external agency under these terms of reference (ToR) is sought as follows:

1) Strengthen supply chain systems by leveraging global procurement mechanisms (e.g., UNICEF services) and providing technical assistance for forecasting, quantification, procurement, and last‑mile distribution of Maternal Multiple Micronutrient (MMS), equipment (Photometer, HemoCue Hb 201 HemoCue Hb 201/ Set) and supplies (Cleaner for Hemo Cue Photometer/PAC- 5 and Microcuvette for HB 201/ Box 200).

2) Enhance service quality and coverage through capacity building of health workers, FCHVs, and managers; improving ANC packages; supporting maternal anemia screening; and establishing digital learning platforms.

3) Support community engagement and behaviour change to promote optimal maternal feeding practices, dietary diversity, maternal nutrition, WASH practices, referral services to ANC/PNC clinics and increased demand for maternal nutrition services.

4) Support in capacity building of health managers, health workers and female community health volunteers of Madhesh Province on maternal nutrition programme including MMS distribution.

5) Strengthen institutional systems by supporting coaching/mentorship systems, developing master trainers, integrating nutrition services into HMIS/PAMS, improving supervision systems, and aligning interventions with existing government platforms.

6) Identify government teaching institutions and universities that can provide the required training on maternal nutrition, and optimal maternal nutrition practices, including the use of the digital platform to deliver training on maternal nutrition including MMS distribution, and ensure that a sustainable system is established.

7) Lead monitoring, evaluation, evidence generation, and coordination through real‑time dashboards, quarterly assessments, coverage tracking, implementation research, documentation of best practices, and support to government-led planning and coordination mechanisms

- bACKGROUND and JUSTIFICATION

Anaemia is defined as decreased blood concentration of haemoglobin (Hb). WHO categorizes anaemia as mild, moderate and severe (WHO, Global Health Metrics). In Nepal prevalence of anaemia in pregnant women aged 15-49 years dropped by 13 per cent point (from 46 per cent in 2016 to 33 per cent in 2022). However, of the total anaemia cases, mild and moderate anaemia remains a public health problem in Nepal since 62 per cent and 38 per cent of pregnant women are suffering from mild and moderate form of anaemia respectively, whereas only 1 per cent of pregnant women are suffering from severe form of anaemia (NDHS 2022). Thirty-eight per cent of maternal anaemia is because of iron deficiency in Nepal. This indicates that dietary iron deficiency is the main cause of anaemia in the country. Moreover, Zinc, and Vitamin ‘A’ and RBC folate deficiency are also contributors of maternal anaemia. According to the Nepal National Micronutrient Status Survey (2016), 24 per cent, 3 per cent and 12 per cent women in the country are suffering from zinc, Vitamin ‘A’ and RBC folate deficiency respectively. Other factors that contribute to the high level of maternal anaemia are blood disorder (4.5 per cent), infections infestation (58.6 per cent).

Among the 7 provinces of Nepal, Madhesh province is the one with highest expected pregnancy 21 percent (Out of 608,996) and, maternal anaemia is also highest: 52 percent (NDHS 2022). Women in this province is facing multiple nutrition challenges: 13.2 percent with short stature, 18.5 percent with thinness (<18.5 BMI) and 22.8 percent with overweight/obesity problem (BMI 25.0). Maternal iron deficiency anaemia 14 percent, maternal zinc deficiency 24 percent, RBC folate deficiency 6 percent and Vitamin A deficiency 7.9 percent (Retinol ≤0.7µmol/L) are synergistically contributing to the high rate of maternal anaemia in this province.

Changing landscape of food system in this province resulting high consumption of sugar sweetened beverage (SSB) (53.0 percent) and unhealthy food consumption (41.5 percent) displacing healthy diet consumption contributing to low minimum diet diversity among women at only 42.8 percent. In Nepal, only 51.1 percent women achieve full continuum of care (4 ANC visits, institutional delivery, and PNC within 2 days) and Madhesh Province is among the lower performing provinces, affected by wealth, education, caste, mobility restriction and cultural norms. Other non-nutritional factors, such as poor hygiene and sanitation, infection and infestation, genetic disorders (sickle cell and thalassemia) and gender-based violence also contributing to the high rate of anaemia in this province. The gynaecological and obstetric data that contributes to the heavy blood loss during menstruation is not available in the country which could justify the reason for high maternal anaemia in Madhesh and requires further exploration through health statistics.

The ultimate result of all these factors contributing to maternal anaemia in Madhesh province is poor birth outcomes including low birth weight (LBW), which significantly increase the risk of child wasting and neonatal mortality in the province. Anaemic mothers are 3.4 times more likely to deliver LBW infants, who are more vulnerable to infections and complications. Wasting in neonates, especially when combined with LBW or prematurity, raises the risk of death up to 11 times. Despite progress in reducing maternal and child mortality nationwide, Madhesh province of Nepal remains off-track to achieve the 2030 SDG targets.

Under this context, Government of Nepal recognized the strong need to address maternal anaemia using package of maternal nutrition intervention including Multiple Micronutrient Supplement (MMS) distribution in Madhesh Province. This intervention is critical to improving neonatal survival in Madhesh Province. However, this is comparatively new intervention area for the country like Nepal where human resource capacity in health still needs to build up to implement this package of intervention working together with the existing health system. It requires external technical agency services to support following actions: (1) strengthen the supply chain management system inclusive of MMS forecasting, quantification, and last-mile distribution to ensure a stockout rate of less than 5%; (2) strengthen continuum of care package for pregnant and breastfeeding mothers using the ANC/ PNC platforms; (3) support maternal nutrition education & counselling and social behaviour change (SBC) action at health facilities and community platforms; (4) build the capacity of health workers and FCHVs rolling out minimum package of maternal nutrition inclusive of MMS distribution, (5) support maternal anaemia screening and gestational weight measurement using ANC platform, (6) monitoring and tracking adherence with maternal MMS among the pregnant and breastfeeding mothers and (7) support to document effective coverage strategies such as case studies, success stories, lesson learned in maternal nutrition programme in Madhesh Province.

In this context, UNICEF Nepal is currently looking for an implementing agency with an excellent track record (nationally) on health system strengthening focussing on human resource capacity building to support the Ministry of Health and Population (MoHP) Nepal for implementation of minimum package of maternal nutrition including maternal MMS distribution in Madhesh Province. Engaging an external technical agency under UNICEF stewardship will ensure that MMS implementation in Madhesh Province is not a standalone intervention, but a strategic investment in sustainable system strengthening, accelerating progress toward equitable maternal nutrition outcomes and neonatal survival while advancing Nepal’s commitments under the SDGs.

- objective:

The objective of this assignment is to provide high‑quality technical assistance to Madhesh Province for the effective rollout, institutionalization, and monitoring of the Minimum Package of Maternal Nutrition—including Multiple Micronutrient Supplementation (MMS) for pregnant women and breastfeeding mothers within government health systems, ensuring improved maternal nutrition services and strengthened provincial and local government capacity.

Specific objectives

1. Strengthen Policy, Planning, and Coordination:

- To support advocacy events in partnership with academia and/or anaemia alliance group to raise awareness about situation of adolescent and maternal anaemia in Madhesh province, factors contributing to the existing prevalence of anaemia and potential solution to reduce it.

- To support the province in operational planning, adaptation of national maternal nutrition guidelines, and integration of the minimum package—including MMS—into provincial and municipal workplans.

- To facilitate multi-sectoral coordination among government, partners, and stakeholders to ensure harmonized implementation.

2. Build Capacity of Health Systems and Workforce:

- To develop and deliver training packages, job aids, and supportive supervision tools for health workers, supervisors, and program managers on maternal nutrition and MMS.

- To strengthen supply chain and logistics management capacity for uninterrupted availability of MMS.

3. Support Implementation of the Minimum Package of Maternal Nutrition:

- To provide technical support for the rollout of counselling, supplementation, screening, and follow-up services across health facilities and community platforms.

- To support integration of maternal nutrition indicators—including MMS—into provincial HMIS and routine monitoring tools.

4. Strengthen Data Systems, Monitoring, and Quality Improvement:

- To establish or enhance mechanisms for data collection, review, and use at province and municipal levels.

- To support implementation of quality improvement processes for maternal nutrition services, including supportive supervision and on-site coaching.

5. Generate Evidence, Learning, and Documentation:

- To document lessons learned, best practices, success stories, and bottlenecks to inform provincial scale-up and national guidance.

- To support periodic assessments, baseline/midline/endline reviews, or special studies as required.

6. Enhance Community Engagement and Demand Generation:

- To develop and support implementation of culturally appropriate communication materials and strategies to improve awareness, acceptance, and use of MMS and maternal nutrition services.

- SCOPE OF WORK:

The assigned consulting agency will be responsible for supporting following areas to roll out MMS programme in Madhesh province:

4. 1 Policy, Planning, and Coordination

The implementing agency will facilitate planning workshops with federal, provincial and municipal authorities. In this process, the implementing agency will support to organise kick start meeting at federal and provincial level to raise awareness among the federal and provincial authorities about anaemia, factors contributing to anaemia, gaps and challenges and MMS as potential solution to resolve the challenges of maternal anaemia in consultation with the Family Welfare Division of DoHS and UNICEF Nepal. The implementing agency will provide technical inputs to integrate maternal nutrition and MMS into routine government plans and budget, following Government of Nepal’s 7 step planning process. Moreover, the institution will support the coordination platforms, technical working groups and stakeholder’s meeting.

4. 2 Capacity Strengthening

The implementing agency will support Nutrition Section of Family Welfare Division to develop/adapt training packages, job aids, and materials for Health Workers and Female Community Health Volunteers (FCHVs), Programme Managers (Chief, Health Section at Province and Local Government), Health Supervisors and Nutrition Focal Persons. Using these training package and job aids, the institution will organise training of trainers (ToT) and onsite coaching for Health Workers (Health Facility In charge and Auxiliary Nurse Midwives) and Female Community Health Volunteers (FCHVs).

4. 3 Service Delivery Support

The implementing agency will support to strengthen service delivery system through enhancing frontline health workers (Health facility in charges and Auxiliary Nurse Midwives (ANMs)) capacity to provide maternal nutrition counselling, gestational weight monitoring of pregnant women, symptomatic anaemia detection and management, distribution and adherence monitoring of MMS and deworming and strengthen integration of maternal nutrition services into ANC/ PNC and outreach clinics.

4.4 Strengthening Supply Chain and Logistics

The implementing agency will assess the supply chain readiness of MMS and identify bottlenecks. It will help to build capacity on forecasting, inventory management and reporting for MMS working closely with the Family Welfare Division and Management Division of Department of Health Services (DoHS).  Also, the institution will coordinate and communicate with federal, provincial and local government logistic systems to ensure consistent availability of MMS tablets.

4.5 Monitoring, Evaluation, and Data Use

The Implementing agency will work closely with the Family Welfare Division and Management Division to strengthen integration of maternal nutrition indicators—including MMS—into web-based Health Management Information System (HMIS) and health system tracking tools at federal, provincial and local government levels. It will facilitate data review meetings at federal, provincial and local government. The implementing agency will support Family Welfare Division of DoHS to update already existing monitoring dashboards in HMIS Section of Management Division checklists and supervision tools related to MMS. In addition, it will organise quality improvement (QI) coaching and facility assessments related to MMS services for pregnant & lactating women.

4. 6 Communication, Community Engagement, and SBC

The implementing agency will support to develop /adapt culturally appropriate Social Behaviour Change and Communication (SBCC) materials. It will support in community mobilisation activities through Female Community Health Volunteers (FCHVs) and local groups to increase the demand of MMS tablets among pregnant and lactating women. It will further provide technical inputs to federal & provincial communication campaigns related to MMS distribution.

4. 7 Documentation and Knowledge Management

The implementing agency will document implementation progress, challenges, and success stories during roll out of MMS programme in Madhesh province. It will produce technical briefs, reports and case studies. In addition, the implementing agency will organize learning events for the policy makers, planners and implementors at federal, provincial and local government. The implementing agency will support to disseminate the key results from the large-scale implementation of MMS programme in Madhesh Province using virtual workshops and face to face dissemination workshops.

- methodology:

The implementing agency needs to follow the following methodology to support Ministry of Health and Population (MoHP) Nepal for   rolling out of minimum package of maternal nutrition (Nutrition education and counselling, iron containing supplement MMS distribution, Deworming, Gestational Weight Monitoring and symptomatic screening of anaemic women) in Madhesh Province.

Key assumptions:

- The implementing agency will provide external master trainers for the Master Training of Trainer (MToT).

- Trainers for the cascade training at federal, provincial and local government will be Government Staffs from the respective federal government, provincial government and local government.

- All daily subsistence allowance (DSA) will be provided as per the Government of Nepal’s regulation and rules.

- All travel expenses will be provided as per the Government of Nepal, Ministry of Finance, Travel Expense Regulation (4rth amendment), BS 2072

- All training cost will be provided as per actual basis.

Under this project, following are the expected role of Federal Government:

- The Federal Government shall establish and maintain an enabling policy environment to support the effective implementation and scale-up of the Multiple Micronutrient Supplementation (MMS) programme.

- The Federal Government shall lead the development of a national roadmap for MMS implementation covering the period 2026–2030, ensuring alignment with national nutrition priorities and strategies.

- The Federal Government shall provide overall strategic guidance to the Ministry of Health and Population, the Provincial Health Service Directorate of Madhesh Province and the implementing agency during the planning and roll-out of the MMS programme.

- The Federal Government shall provide feedback/input to implementing agency to harmonize facilitator guideline, health worker guideline, training material and social behaviour change communication (SBC) tool.

- The federal government shall provide official communication letter addressing to Provincial Government and Local Government for supporting implementing agency to deliver the task under this terms of reference (ToR) while rolling out MMS programme in Madhesh Province.

- The federal government shall organise Nutrition Technical Committee (NUTEC) meeting to endorse key decisions related to roll out of MMS programme and also, sharing the key findings from the roll out of the programme in Madhesh Province.

- The Federal Government shall ensure the timely procurement and supply chain management of MMS and other essential commodities, including the distribution to all 136 local governments, in coordination with the Provincial Health Service Directorate of Madhesh Province, implementing partners, and UNICEF Nepal.

- The Federal Government shall oversee the analysis and synthesis of programme-related data, including data generated through DHIS/HMIS systems, with technical support from the implementing agency.

- The Federal Government shall facilitate reporting and knowledge sharing, including the presentation of key findings, progress, and lessons learned during annual national nutrition review meetings.

Expected role of UNICEF:

- UNICEF shall provide technical assistance to the Government of Nepal, including Provincial Governments, through the designated implementing agency to support the effective implementation of the MMS programme.

- UNICEF shall ensure effective communication and coordination with Federal and Provincial Government counterparts through its designated focal persons, including the Nutrition Officer (Middle Childhood, Adolescent and Maternal Nutrition) and the Nutrition Officer at the UNICEF Field Office in Janakpur.

- UNICEF shall facilitate the transfer and application of global evidence and best practices on MMS implementation to Federal and Provincial Governments to strengthen the quality and effectiveness of maternal nutrition programmes in Madhesh Province.

- UNICEF shall ensure the timely procurement of MMS, facilitator & health worker guideline, training materials, job aids and SBC materials that require for the roll out of MMS programme in Madhesh Province to deliver it on time to central medical store (CMS), Pathlaiya.

- UNICEF shall oversee and supervise the implementation of activities outlined in this Terms of Reference (ToR), ensuring adherence to agreed standards, timelines, and deliverables.

- UNICEF shall ensure the timely and efficient execution of programme activities in accordance with the agreement established with the implementing agency.

5. 1 Policy, Planning, and Coordination

The institution should support federal government, provincial & local governments of Madhesh Province in organizing advocacy, planning and coordination meetings to roll out maternal nutrition programs inclusive of maternal micronutrient supplements. This is achieved through organizing advocacy, planning and coordination meetings at federal, provincial and local government prior to capacity strengthening activities in all 3 tiers of government.

- Advocacy, planning and coordination meeting at Federal Government:

Desk reviews the existing situation of maternal anemia, factors contributing to maternal anaemia, national policy on maternal nutrition & reducing anaemia and supports update/ revising guidelines for MMS adoption. In addition, the institute supports Nutrition Section of Family Welfare Division to development of MMS implementation plans, standards and protocols as per need based on the mapping and identification of gaps and challenges in this area. Finally, assist to organize at least one advocacy, planning and coordination meeting for reducing maternal anemia to kick up the MMS rollout in Madhesh Province of Nepal (list of participants in Annex 1.1).

The one-day advocacy, planning and coordination meeting at federal level (Venue: Inside Kathmandu Valley) will be facilitated by the team leader of the implementing agency as facilitator. There will be 55 participants in this meeting. The participants of the meeting will be eligible to receive transportation fee (Taxi fare) as per the government practice for the day of travel. They will also receive day workshop package and stationaries during the meeting time.

- Advocacy, planning and coordination meetings at Madhesh Province:

Following the federal advocacy, planning and coordination meeting, the institution coordinates with the provincial health service directorate to develop provincial MMS implementation plan in line with the kick up meeting at the federal government to ensure provincial ownership on the MMS implementation plan at Madhesh province. To achieve this, the institution will organize provincial advocacy, planning and coordination meetings in Madhesh province (list of participants on Annex 1.2).

The one-day advocacy, planning and coordination meeting at Province level (Venue: Provincial Headquater of Madhesh Province) will be facilitated by two facilitators (one from the implementing agency and another from Government Officials from Federal Government). The facilitators will receive paper presentation cost, daily sustitence allowance and travel allowance as per the government regulation. In addition, there will be 56 participants in this meeting. These participants will receive DSA, transportation fee (Taxi fare), non- residential package and stationaries.

- Advocacy, planning and coordination meeting at 136 local government:

The institution supports the integrate MMS rollout into annual local government plan using 7 steps planning process and develops micro-planning for capacity building and distribution of MMS through health facilities, Antenatal/Postnatal Clinics, FCHVs aligning with the provincial MMS implementation plan. It will support the advocacy efforts with the local government representatives to understand the local causes that contribute to anaemia and potential innovative solutions like MMS to resolve the maternal anaemia challenges in the municipality (local government) (List of participants on annex 1.3).

The one-day advocacy, planning and coordinating meetings at local government will be held in all 136 local governments of Madhesh province. These meetings will be facilitated by one Government Officer from the Provincial Health Service Directorate, Madhesh Province in each local government. The facilitator will receive one day daily subsistence allowance (DSA) and transportation fee (Bus/Taxi fare) as per government regulation. Besides, there will be tentative 31 participants in each local level advocacy, planning and cordination meeting. These participants will be eligible to receive transportation fee (Bus/Taxi fare), day meeting package and stationery for the day of the meeting.

Altogether, there will be 136 local government level advocacy and planning meetings at Madhesh Province. Tentative 31 participants will be at this meeting, and the selected service provider will arrange all logistic costs for this meeting.

5.2 Capacity Strengthening

The implementing agency should support federal government, provincial & local governments of Madhesh Province capacity strengthening of Health Offices at all 3 tiers of government and community-based platforms using cascade training and on-site coaching & mentoring activities. The methodology followed in capacity strengthening in 3 tiers of government is as follows:

- Capacity strengthening in federal government:

The implementing agency will revise/update the existing training curriculum, job aids and information, education and communication materials related to MMS implementation to tailor it for the Madhesh province in close coordination with the Nutrition Section of Family Welfare Division  using the Nutrition Technical Committee (NUTEC) platform inside the Ministry of Health and Population (MoHP) Nepal  Also, the training coordinator of  implementing agency will facilitate to develop facilitator’s guideline and health worker’s guideline on maternal nutrition inclusive of MMS distribution working together with the Nutrition Officer of UNICEF and Chief Nutrition Section of Family Welfare Division.

Once it is developed, the implementing agency will support Family Welfare Division to develop at least 30 lead trainers (Government Staff) from federal government to support the roll out of maternal nutrition program focusing on MMS implementation at Madhesh province. It will support organizing 3 days maternal nutrition program (inclusive of MMS distribution) training to lead trainers at Kathmandu, the capital city of federal government.

To develop lead trainers, the implementing agency will assign a training expert for 3 days where the facilitator will train the lead trainers. The facilitator will receive 3 days DSA and travel allowance as per government regulation. During the lead trainer’s training, there will be 30 participants. These participants will recieve day workshop package during the training days along with stationery.

- Capacity strengthening in Provincial Government:

The implementing agency under the close coordination, communication and collaboration with the Nutrition Section of Family Welfare Division will support in capacity strengthening activities at the Madhesh Province.

In this process, it will organize a day stakeholder’s orientation meeting at Janakpur, the provincial capital of Madhesh Province. Implementing agency will mobilize a government official from federal level to facilitate the stakeholder’s orientation. The facilitator will present a paper during the orientation programme. The facilitator will receive DSA and travel allowance as per the government regulations.

Key participants of these stakeholder’s orientation meeting will be 3 officials from Provincial Ministry of Health and Population (MoHP), Health Directorate & Provincial Health Training Center, 4 officials from Provincial Health Logistics Management Center, 1 official from Provincial Health laboratory, 3 participants from Federal and Provincial Hospitals and 10 stakeholders from MSNP programme, media and academia sector. Altogether, there will be 20 participants in the provincial stakeholder’s orientation meeting. The participants of the one-day stakeholder’s orientation will receive DSA and transportation fee (Taxi/ Bus) as per government regulation. In addition, they will receive non-residential packages and stationery for the day of participation in the stakeholder’s orientaiton meeting.

The implementing agency will further coordinate, communicate and collaborate with the Provincial Health Service Directorate to organize 3 days training of trainers (ToT) to develop 60 provincial trainers at Madhesh Province on maternal nutrition inclusive MMS distribution. One Government Official from Federal Government and one training coordinator from the implementing agency will present papers during the 3 days training of trainers at Madhesh Province. The facilitators will receive DSA and travelling allowance as per the government regulation. In this  training, there will be 60 participants comprising  Director and Nutrition Focal Person of Provincial Health Service Directorate, Chief and Training Officer of Provincial Health Training Center, Chief of Health Offices and Nutrition Focal Person /Public Health Officers of Provincial District Health/Public Health Offices, Nutrition Officers from different partner agencies working in the Province and at least 30 lead trainers with public health and nutrition background from Madhesh Province. Later, these trainers will mobilize in sub-national level capacity building events at Madhesh Province. These participants will receive DSA, travel allowance (round trip), non-residential workshop package, and stinaries during the day of trainig.

In addition, the implementing agency will support the Provincial Health Service Directorate to organize a three-day provincial district level training for Chief Health Section and Nutrition Focal person of Health section of all 136 Municipalities under 8 districts. and Nutrition officers from different NGOs . The training will be organized in 8 batches. In each batch, there will be at least 14 participants. Altogether there will be 272 participants in the provincial district level training. The implementing agency will organise this training at Janankpur, the provincial capital city of Madhesh Province. Key facilitator for this training will be 8 provincial trainers. The provinical trainers will present papers in the 3 days training events. They will receive DSA and travelling allowances as per government regulation for the training days. 272 participants of this training will also receive DSA and travel allowance as per the government rule. In addition, they will receive non-residential packages and stationery for the 3 days training days.

Besides, the implementing agency will support the provincial health service directorate to update supportive supervision tools and checklists and use of these tool kits & checklists during technical support visits (TSVs) in 136 local government while rolling out the maternal nutrition program inclusive of MMS distribution.

- Capacity strengthening at 136 Local Government:

The implementing agency will further communicate, coordinate and collaborate with the 136 Local Government to organize one day stakeholder’s orientation focusing on members from Nutrition and Food Security Steering Committee and key influencers that support promotes maternal nutrition from municipality level. In each local government, one facilitatator from the Provincial Health Service Directorate of Madhesh Province will present paper on maternal nutrition programme inclusive of MMS distribution. The 136 facilitators will receive DSA and travel allowance as per the government regulation. In these stakeholders’ orientations, there will be 31 participants. These participants will receive transportation fee (Taxi/Bus), day meeting package and statinary for the day of stakeholder’s orientation programme. Altogether 31 participants of the local government will participate in this stakeholder’s orientation.

Upon completion of the stakeholder’s orientation, the implementing agency will further support the local government to build the capacity of Health Workers (Senior Health Assistant, Health Assistant, Auxillary Nurse Midwives, Nursing Staffs) on maternal nutrition programme inclusive of MMS distribution through 3 days capacity building training. These health workers run ANC/PNC clinics at Health Facilities. The implemening agency will mobilise one trainer per batch from the provincial health service directorate to build the capacity of these health workers in 20 batches of training, each batch containing at least 20 health workers. All together, there will be 408 health workers   comprising 136 Senior Health Assistant (SHA)/ Health Assistant (HA), 136 Auxillary Nurse Midwives (ANMs), 136 Nursing staffs in municipality level training to deliver maternal nutrition services inclusive of MMS distribution. The facilitator for this training will present papers on maternal nutrition, covering topics like maternal nutrition services, MMS counselling, dosage, side effect management, follow-up, recording, reporting and stock management. The facilitator will receive DSA and transportation allowance as per the government regulation for the day of training.  The participants of the training will receive DSA and transportation allowance as per the government regulation for the day of training. In addition, they will receive day meeting package and stationery on the day of training.

Upon completion of municipality level training, the institution will further support the health facilities to organize one day orientation for 1688 health workers, working in 33 Primary Health Care Center, 748 Health Post, 40 Urban Health Clinic Center, 242 Basic Health Service Center of Madhesh Province. The orientation will be organised in 86 batches, each batch containing 20 participants. The facilitator for the orientation will be Chief of Health Section/ or Nutrition focal person from local government. The facilitator will present a paper on maternal nutrition programme inclusive of MMS distribution during the orientation. The facilitator will receive DSA and travel expenses (Taxi/Bus) as per government regulation for the day of orientation. The participants of the orientation will recieve DSA and travel expenses (Taxi/Bus) as per governmetn regulation for the day of orientation. In addition, they will receive day meeting packages and stationery on the day of orientation.  This orientation will keep all health workers informed about the maternal nutrition programme inclusive of MMS distribution and garner support from them during its implementation.

Besides, the implementing agency will support the local government to build the capacity of 7645 Female Community Health Volunteers (FCHVs) to refer the pregnant women in the health facilities/ANC/PNC clinics to receive maternal nutrition services including MMS tablet through organising 3 days capacity building training to FCHVs. All 7645 FCHVs will receive this capacity building training in 417 batches, covering 20 FCHVs in each batch.  The Health Facility Incharge from the local health facility will be facilitator for the FCHV training programme on maternal nutrition inclusive of MMS distribution. The facilitator will present papers on maternal nutrition inclusive of MMS distribution and train them on maternal nutrition counselling to refer pregnant and lactating women for maternal nutrition services inclusive MMS distribution in near by health facilities. They will be able to follow up the pregnant & postpartum mothers to re-confirm adherance with the MMS dosing.

These trained 7645 FCHVs will organize a one-day mother’s group meeting on the theme area, “Maternal nutrition inclusive of MMS distribution” to 151,461 mothers at least one time during the programme implementation period to keep pregnant and lactating women aware about the importance of MMS for them and their positive birth outcome (preventing low birth weight babies). At least, 7645 mother’s group meetings will be held in the Madhesh Province during the MMS programme implementation, covering 20 mothers per mother group meeting. All FCHVS will receive FCHVs allowance as per the Ministry of Health and Popualation (MoHP), Government of Nepal regulation. All pregnant and lactating mothers participating in the mother’s group meeting will be provided day snack during the mother’s group meeting day as per the government regulation.  The table on annex 1.4 reflects the capacity building events that is expected to be supported by the implementing agency at federal, provincial and local governments level.

5. 3 Service Delivery Support

The implementing agency will support to strengthen service delivery system through enhancing frontline health workers (Health facility in charges and Auxiliary Nurse Midwives (ANMs)) capacity to provide maternal nutrition counselling, gestational weight monitoring of pregnant women, symptomatic anaemia detection and management, distribution and adherence monitoring of MMS and deworming and strengthen integration of maternal nutrition services into ANC/ PNC and outreach clinics. To achieve this, the implementing agency follows the following methodology to support the federal, provincial and local governments of Madhesh Province.

- Service delivery support to federal government:

The implementing agency ensures national integration of MMS into ANC and community health service delivery protocols. It supports to revise/update the “National Medical Standard for maternal and newborn care, volume III, Government of Nepal, Ministry of Health and Population, Department of Health Services, Family Welfare Division, 2022”  through developing supplementary protocol to be added in the main standard document later on for  ensuring maternal nutrition package inclusive of MMS well reflects in the document under large program context.

The implementing agency will assign a maternal and newborn health and nutrition (MNHN) expert for 60 days (maximum) to be assigned for the purpose of supporting the Family Welfare Division to revise/update the national medical standard to incorporate MMS in large scale implementation context. The implementing agency will provide contract paper with the expert to UNICEF as part of deliverables. The expert will receive renumeration fee for he/she/their services as per government regulation. The expert will support organizing at least two meetings of Maternal and Newborn Health Technical Working Committee/ Nutrition Technical Committee in Family Welfare Division to discuss and revise/update the medical protocol. In these meetings, there will be at least 18 government officials from various concern divisions of Department of Health Services in each meeting.  The government officials will receive transportation fee (Taxi fare) as per government regulation in the meeting days. Also, they will receive day lunch pack and stationery on the day of meeting.

The participants of the maternal and newborn health technical working committee/ nutrition technical committee meeting are provided in annex 1.5.

- Service delivery support at provincial government:

The implementing agency ensures MMS distribution well integrates into the provincial ANC/ PNC protocols and helps in addressing provincial level bottlenecks in service readiness.  For this purpose, the maternal and newborn health and nutrition (MNHN) expert of the implementing agency will support at least 1 meeting at Madhesh Province to update ANC/PNC protocols.  Government officials from the Family Welfare Division will facilitate the meeting. The facilitator will present paper on the existing ANC/PNC protocol, organised discussion on the update/ revision requires considering the MMS programme implementation and suggest a corrective action to keep MMS service system ready to address the multiple micronutrient supplement need of pregnant and lactating women. The facilitator will receive DSA and travel expenses as per the government regulation for the day of meeting. There will be 26 government officials participating in this meeting. They will recieve DSA and travel expenses (Taxi fare) as per the government regulation for the day of meeting. In addtion, all participants will receive snacks (lunch pack) and stationery for the day of meeting. The participants of the ANC/PNC protocol meeting at province level for MMS distribution is as per annex 1.6.

- Service delivery support at local government:

The implementing agency provides support to Chief, Health Section, Local Government to ensure routine and outreach ANC platforms dispense maternal micronutrient supplements (MMS) and mobilizes Female Community Health Volunteers to provide community follow up for the adherence of MMS through home visits. At least one time, 7645 Female Community Health Volunteers in Madhesh Province will be mobilized in door-to-door household visit to identify the pregnant women at community level and refer them to nearest health facility to receive maternal nutrition services inclusive of MMS tablet. FCHVs will receive one-time FCHV allowances for these services as per government regulation. The number of FCHVs planned to mobilize for referral services to pregnant and lactating women at ANC/PNC services is as per annex 1.7.

5. 4 Strengthening Supply Chain and Logistics:

It will be achieved through following methodology:

- Strengthening supply chain and logistics at federal government:

The implementing agency will assign a supply chain and logistics management expert for 120 days to support Management Division of DoHS to forecast annual MMS needs for nationwide procurement with special focus to Madhesh Province. The expert will support the Family Welfare Division of Ministry of Health and Population to manage MMS procurement and its distribution to Madhesh Province. The implementation agency will provide contract documents with the supply and logistic management expert to UNICEF as part of deliverables.  Please refer to annex 1.8 for logistic expert support for quantification of MMS at federal government.

- Strengthening supply chain and logistics at provincial government

The implementing agency supports the one-day provincial level forecasting and distribution planning meeting mobilizing the logistic expert assigned at federal level. 2 Government Officials (one from Family Welfare Division and another from Management Division) will present paper on forecasting of MMS commodity and supply planning of MMS commodity in Madhesh Province and discuss the key issues and challenges on supply chain management and distribution practices and corrective action that can be taken to resolve the challenges. The facilitators will receive DSA and travel expenses as per government regulation. In this meeting, there will be 14 government officers as participants. These participants will receive DSA and transportion fee (Taxi fare) for the day of meeting. In addition, they will also receive non-residential packages and stationery during the meeting day. Please refer to annex- 1.9 for the expected number of participants in the forecasting and supply planning meeting at Madhesh Province.

- Strengthening supply chain and logistics at local government:

The implementing agency will support building the capacity of logistic staff at local government on MMS storekeeping and inventory management through organising one day logistic management training at local government to ensure 136 municipal stores and sub-ordinate health facilities under it maintains accurate account of MMS distribution and stock records. It will engage with the health institution to ensure timely replenish request for MMS will be placed via e-LMIS/ PAMS. The one-day logistic management training will be organised in 7 batches covering 136 staff looking at the logistic issues at local government. In each batch of training, there will be 20 staff from local government. One Government officer from Provincial Health Service Directorate will present paper related to logisic management related issues focussing on MMS distribution in each batch of training. These facilitators will receive DSA and travel expenses as per government regulation. In this training, 136 staff looking after storage, handling and distribution of MMS at local government will participate. They will receive DSA and travel expenses (taxi fare/ bus) as per the government regulation. In addition, they will receive day meeting package and stationery on the training day. Please refer to annex 1.10 for the participants in the one-day logistic management training to logistic staff at local government.

5. 5 Monitoring, Evaluation, and Data Use

The implementing agency will work closely with the Family Welfare Division and Management Division to strengthen integration of maternal nutrition indicators—including MMS—into web-based Health Management Information System (HMIS) and health system tracking tools at federal, provincial and local government. It will facilitate data review meetings at federal, provincial and local government. It will support Family Welfare Division of DoHS to develop monitoring dashboards, checklists and supervision tools related to MMS. In addition, it will organize quality improvement (QI) coaching and facility assessments related to MMS services for pregnant & lactating women.

- Monitoring, evaluation and data use at federal government:

The implementing agency will support the Family Welfare Division to integrate MMS indicators into e-HMIS/ e-LMIS to ensure the coverage and compliance of MMS among the pregnant & lactating women could be monitored through the existing monitoring platform. At achieve this, it will support organizing a Nutriton Technical Working Group (NUTEC) meeting to discuss around MMS indicator to be incorporated in regular DHiS/ IHIMS. There will be 10 participants in the meeting. The participants of the meeting will receive travel expense (taxi fare) as per the government regulation for the meeting day. Also, a day snack (Lunch pack) and stationary will be provided to the participants on the meeting day. Besides, the implementing agency will support the HMIS Section to analyze the MMS monitoring data through already existing national dashboard. Please refer to annex 1.11 for the participants in the one-day M & E meeting on MMS monitoring at federal level.

The implementing agency will further support to 2 government officials from federal level to visit the MMS programme implementation areas in Madhesh Province at least 6 times a year with each visit time for approximately 7 days. The Government officials will receive DSA, travel expenses and other miscellaneous expenses (vehicle rental) for local travel as per the government regulation.  The purpose of this visit is supervising and monitoring the MMS programme implementation, providing technical backstopping and, taking corrective action on the issues and challenges observed at the field level programme implementation from the federal level.

- Monitoring, evaluation and data use at provincial government:

The implementing agency will support the 14 Government Officials from provincial health service directorate to conduct 12 technical support visits (TSVs) with maximum 3 days in MMS programme implementation area focusing on the MMS indicators. The Government officials will receive DSA, travel expenses and other miscellaneous expenses (vehicle rental) for local travel as per the government regulation.  The purpose of this visit is supervising and monitoring the MMS programme implementation, providing technical backstopping and, taking corrective action on the issues and challenges observed at the field level programme implementation from Provincial Health Service Directorate of Madhesh Province. The implementing agency will also support analyzing the provincial trends on MMS distribution, identify coverage gaps and suggest corrective action. It will monitor the data quality and provide feedback to 136 local governments. Please refer to annex 1.12 for the officials from provincial governments who will be taking part in the technical support visit (TSVs).

- Monitoring, evaluation and data use at local government:

The implementing agency will support the Chief of Health, Local Government in 136 local governments to conduct one day technical support visits (TSVs) for at least 6 times a year at 1063 health facilities (33 PHC, 748 Health Post, 40 Urban Health Clinic, 242 Basic Health Center), focusing on the MMS indicators to ensure timely and accurate recording of MMS distribution, coverage and adherence. The Chief of Health Section, Local Government, will receive DSA, travel expenses and other miscellaneous expenses (vehicle rental) for local travel as per the government regulations. During the visit, the implementing agency will facilitate holding 136 monthly review meetings at local government to discuss on MMS programme performance based on the performance indicators. Please refer to annex 1.13 for the officials from local governments who will be taking part in the technical support visit (TSVs).

5. 6 Communication, Community Engagement, and SBC

The implementing agency will support designing and developing culturally appropriate Social Behaviour Change and Communication (SBCC) materials and training materials in consultation with UNICEF SBC section using methodologies as listed below:

- Communication, community engagement and SBC at federal government:

The implementing agency will support to Nutrition Section of Family Welfare Division (FWD) to adapt existing materials from Implementation Science Research on MMS and also help to design and develop culturally appropriate Social Behaviour Change and Communication (SBCC) materials (MMS distribution guidance note  – Statistical Information Collection support material (A4 size, 4 pages), MMS reminder calendar (A4 size), MMS brochure (A4 size) for mothers) and training materials ( Facilitator guideline for MMS distribution for health workers (A3 Size, 8 pages, MMS flip chart (A4 size, 34 pages), MMS registers (A4 size), MMS forms (A4 Size), Maternal Nutrition Card (A4 Size), MMS Reference Manual (A4 Size)) at federal level. In addition, the implementing agency will support developing communication messages for the development of communication materials for radio PSAs and digital content. It will provide technical inputs to federal and provincial communication campaigns related to MMS distribution. For the purpose, the implementing agency will depute a SBCC and training material designer for 60 days who will closely work with the Nutrition Section of Family Welfare Division and SBCC Section of UNICEF Nepal. The implementing agency will share the contract document with SBCC and training material designer as part of the deliverable. Please refer to annex 1.14 for the number of SBCC and training material development expert engaged at federal level to design and develop SBCCC and training materials.

The SBCC and training material designer of the implementing agency will support to organise 2 Nutrition Technical Committee (NUTEC) meeting to finalise the SBCC and training material to roll out maternal nutrition programme inclusive of MMS distribution in Madhesh Province. In this NUTEC meeting, there will be at least 40 participants in each meeting. The participants of the meeting will receive travel expense (taxi fare) as per the government regulation on the day of the meeting. In addition, they will also receive day snack (lunch pack) and stationery on the day of the meeting.

- Communication, community engagement and SBC at provincial government

The implementing agency will support the Provincial Health Service Directorate to adapt national message on maternal nutrition inclusive of MMS distribution to local language. Also, engages provincial media and community radios to promote the maternal nutrition message including importance of MMS for pregnant and lactating women. For this purpose, the implementing agency will depute a SBCC and training material designer, knowledgeable about local language of Madhesh Province for 60 days who will closely work with the Health Service Directorate of Madhesh Province and UNICEF Field Office, Janakpur.

The implementing agency will share the contract document with the SBCC and training material designer, knowledgeable about local language of Madhesh Province with UNICEF as part of the deliverable. SBCC and training material designer will support to organise 2 Provincial Nutrition Technical Committee (NUTEC) meeting of Madhesh Province to adapt and finalise the SBCC and training material in local language of Madhesh Province to roll out maternal nutrition programme inclusive of MMS distribution in Madhesh Province. In this provincial NUTEC meeting, there will be at least 40 participants in each meeting.

The participants of the meeting will receive travel expense (taxi fare) as per the government regulation on the day of the meeting. In addition, they will also receive day snack (lunch pack) and stationery on the day of the meeting. Please refer to annex 1.15 for the number of SBCC and training material development expert engaged at province level to design and develop SBCCC and training materials focusing on Madhesh Province.

- Communication, community engagement and SBC at 136 Local Government

The implementing agency will support the 136 local government to train frontline workers (Health facility Incharge and Auxiliary Nurse Midwives) to effectively communicate with the pregnant women and breastfeeding mothers on maternal nutrition practices and adherence to MMS distribution using interpersonal communication (IPC) tool during the ANC/PNC visits.  The implementing agency will provide a one day on-site couching to health facility in charges and Auxillary Nurse Midwives (ANMs) on the counselling skills on maternal nutrition and MMS distribution. The implementing partner will mobilize an onsite couching counsellor from federal level to provide on-site coaching on MMS distribution to health workers and ANMs in 1063 health faclities. The onsite couching counsellor will practically demonstrate the counselling skill to the health workers for a day in each health facilties. The onsite couching counsellor will receive DSA and travel expenses as per the government regulation for both regional travel and local travel.

In addition, the implementing agency will support building the capacity of 7645 FCHVs to conduct household level counselling and organize mother’s group meetings to increase awareness about the importance of maternal nutrition and MMS adherence for healthy baby born. The implementing partner will mobilize an onsite couching counsellor from federal level to provide on site couching on MMS distribution to 7645 Female Community Health Volunteers (FCHVs) in 1063 health faclities. The onsite couching counsellor will practically demonstrate the interpersonal communication technique to Female Community Health Volunteers (FCHVs) for raising awareness about maternal nutrition services and importance of MMS among pregnant and lactating women and then refer them to nearest health facility to receive the matenral nutrition services. The onsite couching counsellor will receive DSA and travel expenses as per the government regulation for both regional travel and local travel. Please refer to annex 1.16 for the number of participants participating in the interpersonal communication (IPC) training at local government.

5. 7 Documentation and Knowledge Management

The implementing agency will document implementation progress, challenges, and success stories during roll out of MMS programme in Madhesh province. While documenting, it will follow following methodology.

The implementing agency will organize learning events for the policy makers, planners and implementors at federal, provincial and local government in Kathmandu with support from UNICEF Center of Excellence. It will support disseminating the key results from the large-scale implementation of MMS programme in Madhesh Province using virtual and face-to-face dissemination workshops.

- Documentation and knowledge management at federal government:

The implementing agency will support the national best practices and success stories in maternal nutrition inclusive of MMS distribution through collecting, compiling, editing and finalizing these best practices and stories from Madhesh Province. It will produce at least one technical brief, one report and 8 case studies. The implementing agency will organize workshops and technical group meetings to share these best practices, success stories and policy briefs. This is achieved through the knowledge generation and management expert deputed for at least 30 days period in the implementing agency. The implementing agency will share the contract document with the knowledge generation and management expert as part of deliverable.  Please refer to annex 1.17 for the number of knowledge generation and management expert (KGME) and government officials participating in the development of technical brief, report, case studies and learning events organized by UNICEF Center of Excellence.

The implementing agency will organize a one-day workshop for sharing best practices in maternal nurition and MMS distribution at federal level. The knolwedge generation and management expert of the implementing agency will facilitate the workshop. In this workshop, 30 participants from Government of Nepal and other nutrition programme stakeholders will participate. The participants of the workshop will receive transportation fee (Taxi fare) as per the government regulation. In addtion, they will receive day workshop package and stationery during the workshop day.

- Documentation and knowledge management at Provincial government:

The implementing agency will support compiling and analyze provincial case studies, innovations and challenges during maternal nutrition programme inclusive of MMS distribution. This is achieved through the knowledge generation and management expert deputed for at least 30 days period in the implementing agency. The implementing agency will share the contract document with the knowledge generation and management expert as part of deliverable. Please refer to annex 1.18 for the number of knowledge generation and management expert (KGME) engage to develop at least 8 case studies from 8 districts of Madhesh province.

- Documentation and knowledge management at 136 local government:

The implementing agency will support community stories, challenges and programme learning during implementation of maternal nutrition programme inclusive of MMS distribution in 139 local governments. This is achieved through the knowledge generation and management expert deputed for at least 90 days period in the implementing agency. The implementing agency will share the contract document with the knowledge generation and management expert as part of deliverable. Please refer to annex 1.19 for the number of knowledge generation and management expert (KGME) engage to develop at least 139 case stories from 139 local government of Madhesh province.

5.8 Dissemination of report on maternal nutrition and MMS distribution programme implementation in Madhesh Province:

At the end of the project, the implementing agency will well document the MMS programme implementation in Madhesh Province and submit draft report to UNICEF. Upon UNICEF’s review and comment over the report, the implementing partner will ensure it’s professional editing by a language editor for 11 days before final report submission. Once the report is finalized, the implementing parter will organise a dissemination meeting of the report at federal level. Government Official from the Family Welfare Division will present a paper on the base of the report in the dissemiantion meeting. In the dissemination meeting, high level officials from Ministry of Health and Population (MoHP), Officials from National Planning Commission and line Ministries, representatives from US Department of State, UNICEF and other partner agencies on nutrition programme are expected to participate. At least 55 Government officials are expected to participate in the dissemination meeting. The participants of the dissemination meeting will receive DSA and travel expenses (Taxi fare) as per government regulation. In addition, they will recieve day workshop package and stationery on the day of dissemination meeting.

- activities, tasks, and expected timeline

| Activities | Tasks | Expected timeline |
| --- | --- | --- |
| Policy, planning and coordination: Desk review of maternal nutrition related global and national documents and submission of the approach paper/inception report to MoHP and UNICEF | - Advocacy, planning and coordination meeting at federal government (55 participants x 1 day) - Advocacy, planning and coordination meeting at Madhesh Province (56 participants x 1 day) - Advocacy, planning and coordination meetings at 136 local government (31 participants x 1 day x 136 LG) | Actual days 3 days, expected to complete all task related to policy, planning and coordination within 30 days upon issuance of purchase order (PO) |
| Capacity Strengthening | - Development of facilitator’s guideline, health worker’s guideline and training package on maternal nutrition inclusive of MMS distribution (1 training material designing expert x 30 days) - Lead trainers training at federal government (30 participants x 3 days) - Stakeholder’s orientation at Madhesh Province (25 participants x 1 day) - Training of Trainers (ToT) at Madhesh Province (60 participants x 3 days) - District level training of trainers (ToT) at Madhesh Province (272 participants x 3 days) - Stakeholder’s orientation at Local government (31 participants x 1 day x 136 Local Government) - Palika level training in 136 local government (3 participants x 3 days x 136 local government) - Health facility level training for Health Workers at health facilities of 136 local government (1688 participants x 3 days) - Community level training for Female Community health volunteers (7645 FCHVs x 3 days) - Empowering mothers through mother’s group meeting (FGD) (151,461 pregnant and lactating women x 1 day) | Actual days 51 days, expected to complete all task related to capacity strengthening within 62 days (two month) after completion of first deliverable. |
| Service delivery support | - Revising/updating National Medical Standard for maternal and newborn care, Volume III, Government of Nepal, MoHP, DoHS, FWD, 2022) with supplementary paper on including MMS in maternal nutrition package at Federal Government (1 Expert x 60 days) - Maternal & Newborn Health Technical Committee/ Nutrition Technical Committee meetings at Federal Government (18 participants x 1 day x 2 times. - Supply readiness and ANC/PNC protocol meeting at province for MMS distribution (26 participants x 1 day) - FCHV mobilisation for house to house visit to refer/ encourage pregnant and lactating women to complete 8 ANC/4 PNC package at local government (7645 FCHVs x 1 day) | Actual days 63 days, expected to complete all task related to service delivery support within 30 days (one month) after completion of 2nd deliverables. |
| Supply chain and logistic system strengthening | - Quantification of MMS and development of distribution plan (1 logistic expert x 60 days) - One day provincial level forecasting and supply planning meeting (14 participants x 1 day) - One day logistic training at 136 local government (136 participants x 1 day). I | Actual days 62 days, expected to complete all task related to service delivery support within 31 days (one month) after completion of 3rd deliverables. |
| Monitoring, evaluation and data use | - M&E meeting on MMS at Family Welfare Division of DoHS (10 participants x 1 day x 4 times) - Technical support visits (TSV) from officials from provincial government to 136 local government (14 participants x 136 LG x 3 days) - Technical support visits (TSV) from Local Government to 1063 Health facilities (1 Health Supervisor x 1063 Health facilities x 3 days) | Actual days 7 days, expected to complete all tasks related to monitoring, evaluation and data use within 30 days (one month) after completion of 4th deliverables. |
| Communication, community engagement and SBC | - SBCC and training material designing and development through mobilising SBCC and training material designing expert at federal government (1 expert x 60 days) - Adaptation of national message on maternal nutrition and MMS distribution in local language of Madhesh Province through mobilising SBCC and training material designing expert at provincial government (1 expert x 60 days) - Interpersonal communication (IPC) training to provide maternal nutrition counselling to Health Workers and Auxiliary Nurse Midwives at Local Government (1063 participants x 2 days) - Interpersonal communication (IPC) training to Female Community Health Volunteers (FCHVs) to organise mother’s group meeting on maternal nutrition inclusive of MMS distribution at Local Government) (7645 FCHVs x 1 day). | Actual days 123 days, expected to complete all task related to communication, community engagement and SBC within 31 days ( one month) after completion of 5th deliverables. |
| Documentation and knowledge management | - Development of one technical brief, one report and 8 case studies (1 Knowledge management expert x 30 days) - Workshop for sharing best practices in maternal nutrition and MMS distribution at federal government (30 participants x 1 day) - Development of one technical brief, one report and 8 case studies of Madhesh Province (1 Knowledge management expert x 30 days) - Development of 136 case stories from 139 local government (1 story writer x 7 days x 136 local government). | Actual days 68 days, expected to complete all task related to documentation and knowledge management within 31 days (one month) after completion of 6th deliverables. |
| Submission of final report on maternal nutrition programme inclusive of MMS distribution in Madhesh Province | - Development of final report (1 report writer x 1 report x 11 days) - Dissemination meeting of report on maternal nutrition and MMS distribution programme implementation in Madhesh Province (1 day) | Actual days 12 days, expected to complete all task related to dissemination meeting and submission of final report within 28 days (one month) after completion of 7th deliverables. |

- DURATION:

The Contract duration is 9 months from signing of contract.

- WORKING LOCATIONS:

The implementing agency can work from its office/workstation in Madhesh Province and should be in close contact with MoHP, Provinical Health Service Directorate of Madhesh Province under Ministry of Health and Population, FWD/Nutrition Section and UNICEF physically when required.

The program will be implemented in 8 districts of Madhesh Province (Saptari, Siraha, Dhanusha, Mahottari, Sarlahi, Rautahat, Bara and Parsa) for maternal nutrition programme including MMS distribution.

- DELIVERABLES:

| No | Deliverable | Estimated number of days required | Estimated Completion Date |
| --- | --- | --- | --- |
| 1 | An inception reports inclusive of detail work plan and advocacy, policy, planning and coordination meetings at federal, Madhesh Province and 136 local government of Madhesh Province (D1) | 30 days | June 2026 |
| 2 | Report on Health Sector’s human resources capacity strengthening in Madhesh Province to deliver maternal nutrition programme inclusive of MMS distribution (D2) | 62 days | August 2026 |
| 3 | Report on strengthening service delivery system in Madhesh Province (D3) | 30 days | September 2026 |
| 4 | Report on supply chain and logistic system strengthening to forecast, quantify and deliver MMS supplements to pregnant and lactating women in Madhesh Province (D4) | 31days | October 2026 |
| 5 | Report on Information System Strengthening to record, report, analysing the data and digital reflection on the progress made on MMS coverage and adherence using dashboard including technical support visits at all three tiers of government (Federal, Madhesh Province and 136 Local Government) (D5) | 30 days | November 2026 |
| 6 | Report on communication, community engagement and SBC to empower pregnant and lactating women for receiving maternal nutrition services and adhere with the MMS compliance (D6) | 31 days | December 2026 |
| 7. | Report on knowledge generation and management inclusive of technical briefs, case studies, best practice sharing workshop (D7) | 31 days | January 2027 |
| 8. | Submission of final report on maternal nutrition programme inclusive of MMS distribution in Madhesh Province (D8) | 28Days | By February 2027 |
|  | Total | 273 days |  |

- PROPOSED PAYMENT SCHEDULE:

| No | Deliverable[1] | Percentage of payment |
| --- | --- | --- |
| 1 | Submission of inception reports inclusive of detail work plan and advocacy, policy, planning and coordination meetings at federal, Madhesh Province and 136 local governments of Madhesh Province (D1) | 16% of Contract Value |
| 2 | Submission of report on Health Sector’s human resources capacity strengthening in Madhesh Province to deliver maternal nutrition programme inclusive of MMS distribution (D2) | 15% of Contract Value |
| 3 | Submission of report on strengthening service delivery system in Madhesh Province (D3) | 10% of Contract Value |
| 4 | Submission of report on supply chain and logistic system strengthening to forecast, quantify and deliver MMS supplements to pregnant and lactating women in Madhesh Province (D4) | 11% of Contract Value |
| 5 | Submission of report on Information System Strengthening to record, report, analysing the data and digital reflection on the progress made on MMS coverage and adherence using dashboard including technical support visits at all three tiers of government (Federal, Madhesh Province and 136 Local Government) (D5) | 15% of Contract Value |
| 6 | Submission of report on communication, community engagement and SBC to empower pregnant and lactating women for receiving maternal nutrition services and adhere with the MMS compliance (D6) | 13% of Contract Value |
| 7 | Submission of report on knowledge generation and management inclusive of technical briefs, case studies, best practice sharing workshop (D7) | 10% of Contract Value |
| 8 | Submission of dissemination meeting and final report on maternal nutrition programme inclusive of MMS distribution in Madhesh Province (D8) | 10% of Contract Value |

[1] Payment for training, Meeting will be done at cost

- CONTRACT SUPERVISION:

The implementing agency will work with MoHP, FWD/Nutrition Section, UNICEF, Provincial Health Service Directorate of Madhesh Province, health Offices and Local levels, and Health facilities under Local Government in Madhesh Province. However, the day-to-day supervision will be done by Nutrition Officer (Middle childhood/ adolescent and maternal nutrition), UNICEF NCO and Nutrition Officer, UNICEF Field Office, Janakpur under the overall guidance of Chief of Nutrition Section, UNICEF Nepal.

- QUALIFICATIONS AND EXPERIENCE REQUIRED:

Experience of undertaking similar assignments:

Minimum Qualification Requirements for implementing agency Vendor

      - Institutional Experience and Technical Capacity:

(1) The implementing agency must demonstrate a minimum of five (5) years of progressively responsible experience in nutrition and/or public health programming in Nepal, preferably in collaboration with government health systems.

(2) The implementing agency should have a team leader who has previous experience to lead and manage implementation of health and nutrition programme with special focus to health system strengthening.

(3) Demonstrated experience in minimum 2 projects in following areas

- Mandatory experience should be demonstrated as follows:

  - Policy Planning & Coordination

  - Capacity Strengthening

- Additionally, at least any two of the following should be demonstrated as desirable experience:

  - Service Delivery Support

  - Strengthening Supply Chain and Logistics

  - Monitoring and Evaluation

  - Communication, Community Engagement, and SBC

(4) Geographic Presence and Contextual Experience; Prior experience working in Madhesh Province is considered a strong asset and will be viewed favourably during technical evaluation, given the complex nutritional and socio￼cultural context of the province.

(5). Referees:

The implementing agency should provide at least 2 referees from the last two organisation which whom the implementing agency recently worked in project related to health and nutrition. In addition, the implementing agency should provide at least 1 referee for the key personnels (team leader, training coordinator, supply and logistic expert, M&E and SBC Coordinator and district coordinators) including CV for reference check purposes. UNICEF supply unit will conduct a reference check for the qualifying implementing agency before contract award.

2. Human Resource composition in Implementing agency:

Experience and skills of the proposed key personnel in implementing agency:

At least 2-3 full time experienced staff members with postgraduate degrees in public health or nutrition. The staff must have at least 5 years professional experience in implementing nutrition and public health programmes in Nepal. They must possess good planning, analytical, capacity building, negotiating, communication and advocacy skills. Prior experience with maternal health and nutrition programme, iron containing supplements (iron folic acid tablet/ maternal multiple micronutrient supplements) distribution will be added advantage.

Qualification of Key personnel/s:

Team leader (1 person):

- Master’s or advance university degree focused on nutrition, epidemiology, global health and implementation science research, Ph. D is preferred

- Minimum 5 years’ experience as a team leader in public health and nutrition

- Fluent in English and Nepali language.

Supply chain and logistics management expert (1 person):

- Master’s in business administration, Public Health and other relevant degree with specialisation in supply chain and logistic management.

- Minimum 5 years’ experience in procurement, supply chain and logistics management.

- Certificates of procurement, Supply chain and logistics management

- Fluent in English and Nepali language.

Training Coordinator (1 person):

- Master’s in public health, nutrition, clinical nutrition or equivalent degree.

- At least 5 years’ experience in capacity building/training in public health and nutrition programme

- Fluent in English and Nepali language.

M&E and SBC Coordinator (1 person):

- Master’s degree in public health, nutrition, clinical nutrition, or a related field.

- At least 3 years’ experience in public health and nutrition programme

- Fluent in English and Nepali language.

Administration and Finance Officer (1 person):

- Master in Business Management (MBA) or equivalent degree.

- At least 5 years’ experience in accounting and finance.

- Fluent in English and Nepali language.

District Coordinators (8 person):

- Bachelors in public health, nutrition, clinical nutrition or equivalent degree.

- At least 2 years’ experience in public health and nutrition programme.

- Fluent in English and Nepali language.

- Application and evaluation process:

In making the final decision, UNICEF considers both technical and financial aspects. The Evaluation Team first reviews the technical aspects of the offer, followed by review of the financial offers of the technically compliant vendors. The proposal obtaining the highest overall score after adding the scores for the technical and financial proposals together, that offers the best value for money will be recommended for award of the contract.

Each valid proposal will be assessed by an evaluation panel first on its technical merits and subsequently on its price. The weight allocated to the technical proposal is 70% (i.e. 70 out of 100 points). To be further considered for the financial evaluation a minimum score of 49 points is required.

Only proposals with a score of 49 or more points in the technical evaluation will be financially evaluated (i.e. the financial proposal will be opened).

The weight allocated to the financial proposal is 30% as per the following: the maximum number of 30 points will be allotted to the lowest technically compliant proposal.

The proposal(s) obtaining the highest score overall after adding the scores for the technical and financial proposals is the proposal that offers best value for money and will be recommended for award of the contract.

- Pre-screening/Responsiveness check:

The proposals will be reviewed on the basis of completion for following documents:

- Submission of Proposal (Technical & financial) in two separate files/ attachment. And to assure that Vendors have not included any financial price in their technical proposal.

- Legal Company Registration / Business Registration

- VAT registration (only for national firm/NGO/INGO (legally authorized to provide business services)

- Tax clearance certificate of last Fiscal Year or extension of timeline for VAT clearance certificate

- Power of Attorney to submit proposal- (applies when joint partner)

- Vendor Registration form (for new vendor)

- Declaration Form (page 3 -5 in the bid form) filled in. (all boxes must be ticked / answered)

- Declaration that Bidders have no Conflict of Interest

- Financial Audit Report for last 2 years.

- Validity of Proposal is provided as per UNICEF Solicitation requirement.

All the required legal documents as mentioned above shall be attached with technical proposal. Proposals for those who have passed the pre-screening will be forwarded for Technical Evaluation.

The Technical Proposal should include but not be limited to the following:

- Methodology

Detailed Methodology / approach to requirement detailing how to meet or exceed UNICEF requirements for this assignment

- Company Profile

Ensure to include information related to the experience of the company as required (Copy of the company registration)

- References

Details of similar assignments undertaken in last three years including the following information:

  - Title of Project

  - Year and duration of project

  - Scope of Project

  - Outcome of Project

  - Reference / Contact persons

- Work Plan

Proposed work plan showing detailed sequence and timeline for each activity and person days of each proposed team member. The proposed work plan should be consistent with the technical approach and methodology, showing your understanding of the TOR and ability to translate them into a feasible working plan.

- Team Composition

Title and role of each team member. It is estimated a team of 6 core members and 30 additional non-key staffs / lead trainers to complete this assignment within stipulated timeline.

- Team leader (max. 1 personnel)

Expected Input:

The team leader will overall manage the project in 8 districts of Madhesh Province through external and internal coordination, communication and collaboration with UNICEF, Federal Government, Provincial Government and 136 local Government at Madhesh Province.  The team leader will oversee all the administrative, financial and technical issues related to the project implementation. The team leader will oversee the planning, execution, and management of the project as per the terms of reference (ToR) signed between UNICEF and the institution. The team leader will communicate and collaborate with the Nutrition Section of Family Welfare Division, Provincial Health Service Directorate, District Health/Public Health Offices all 136 Local Government to execute the implementation of proposed activities in the project like advocacy, planning and coordination meetings, capacity strengthening, service delivery support, monitoring, evaluation and data use, communication, community engagement and SBC and documentation and knowledge management.  The team leader will monitor the project implementation and ensure quality report is submitted to UNICEF Office. The team leader is also responsible to provide regular update on the programme implementation – a monthly virtual update with short summary – not more than five pages report on progress and challenges. The expected input from the team leader is 273 man-days.

- Supply Chain and logistics Management Expert (max 1 personnel)

Expected input:

The supply chain and logistic is expected to build the capacity of Management Division of Department of Health Services to forecast annual MMS needs for nationwide procurment with special focus to Madhesh Province. The expert will support the Family Welfare Division of Ministry of Health and Population to manage MMS procurment and its distribution in Madhesh Province. It will support to organize one day provincial level forecasting and distribution planning meeting. Also, it will support the building the capacity of logistic staff at local government on MMS storekeeping and inventory management to ensure all 136 municipal stores and subordinate helath facilities under it maintains accurate account of MMS distribution and stock records. It will help in capacity building of health institution to ensure timely replinish request of MMS through placing orders using e-LMIS/ PAMS. The expected input from the supply chain and logistic expert is 131 man-days.

- Training Coordinator (max 1 personnel)

Expected input:

The training coordinator will coordinate overall capacity building activities under the project. The training coordinator will support the team leader and project coordinator to design capacity building plan of human resources of health sector in all 3 tiers of government, identify and recruit lead trainers and execute the capacity building training, mentoring and onsite couching under the project.  The training coordinator will be responsible for identifying at least one or two institute / Institutions to provide training in the future, identify their capacity needs, designing, delivering, and overseeing high￼quality training sessions to build the capacity of project staff and beneficiaries. The training coordinator will develop training materials, ensure alignment with project objectives, and apply effective adult￼learning methodologies. The training coordinator’s role includes mentoring field trainers, monitoring training quality, and providing technical guidance. The training coordinator assesses learning needs, evaluate training outcomes, and recommend improvements to strengthen project impact. The expected input from the training coordinator is 150 man-days.

- M&E and SBC Coordinator (max. 1 personnel):

Expected input:

The M&E and SBC coordinator will be responsible for strengthening monitoring, evaluation and data use activities under the project and documenting the key learning, best practices and case stories from the project sites. The coordinator will lead to develop SBC materials for the project in coordination with the Nutrition Section of Family Welfare Division, Provincial Health Service Directorate, District Health/Public Health Offices and UNICEF Office. The expected input from the project coordinator is 182 man-days

- Administration and Finance Officer (max. 1 personnel):

Expected input:

The Administrative and Finance Manager will be responsible for overseeing all financial planning, budgeting, and reporting processes within the project to ensure accountability and compliance within the terms of reference. The manager will manage administrative operations, including procurement, logistics, and office coordination, to support smooth project implementation. The manager will ensure proper financial controls, monitors expenditures, and prepares timely financial statements and reports in line with UNICEF requirements. The manager will coordinate with project staff, government partners, and UNICEF to meet reporting requirements. Additionally, the manager will supervise administrative teams and maintain efficient systems for documentation, asset management, and audits under the project. The expected input from the administrative and finance officer is 273 man-days.

- District Coordinator (max. 8 personnel):

Expected input:

The District Coordinators will be responsible for coordination, communication and collaboration with the Health Managers of Provinical District Health/ Public Health Offices, 136 local government and Health facilities under these local governments to execute the implementation of proposed activities under the project like advocacy, planning and coordination meetings, capacity strengthening, service delivery support, monitoring, evaluation and data use, communication, community engagement and SBC and documentation and knowledge management. The expected input from the project coordinator is 167 man-days from each coordinator with total man days 1336 from all 8 district coordinators.

- Field trainers:

Expected input:

The field trainers will be responsible for delivering hands‑on training and coaching to human resources in health at federal, provincial and local government. They will implement training curricula, ensure sessions are practical and engaging, and adapt content to the community context. Field Trainers closely monitor participant progress, provide continuous support, and gather feedback to improve training quality. They also coordinate with training coordinator and project teams, maintain accurate records, and contribute to achieving project targets through effective capacity-building. Overall, the field trainers will facilitate the capacity building activities at federal, provincial and local government following the standard training materials designed for the project.

- CV’s

CV of each team member (including qualifications and experience). Ensure to include information related to the qualifications and experience of each proposed team member as required.

The Financial Proposal should include but not be limited to the following:

Bidders are expected to submit a lump sum financial proposal to complete the entire (as per instruction given under Section financial proposal). In order to arrive at the lump sum offer for a given sample size, the firm may work out the budget detail as below:

- Resource costs

Daily rate multiplied by number of days of the experts involved in the study.

- Conference or workshop costs (if any)

Indicate nature and breakdown if possible

- Travel Costs

All travel costs should be included as a lump sum fixed cost/ as per actual. However, the bidder has to present the detail breakdown of transportation cost.

For all travel costs, UNICEF will pay as per the lump sum fixed costs provided in the proposal.

A breakdown of the lump sum travel costs should be provided in the financial proposal. Please note that i) travel costs shall be calculated based on economy class fare regardless of the length of travel and ii) costs for accommodation, meals, and incidentals.

- Any other costs (if any)

Indicate nature and breakdown

Full marks are allocated to the lowest priced proposal. The financial scores of the other proposals will be in inverse proportion to the lowest price.

Bidders are requested to provide a detailed cost proposal – Financial Proposal, factoring in all cost implications for the required services. A special discount or lower rates can be offered for this specific assignment, if applicable.

- EVALUATION WEIGHTING CRITERIA:

Cumulative Analysis will be used to evaluate and award proposals.  The evaluation criteria associated with this TOR is split between technical and financial as follows:

Weightage for Technical Proposal = 70 %

Weightage for Financial Proposal = 30 %

Total Score = 100%

a. Technical Proposal:

The technical proposal should address all aspects and criteria outlined in this Request for Proposal.

| The Technical Proposals will be evaluated against the following: |  |  |
| --- | --- | --- |
| REF | CATEGORY | POINTS |
| 1 | Overall response: - Completeness of response- mandatory (failure of submitting required documentation mentioned in the ToR lead to incompleteness) - Overall correspondence between RFP requirements and proposal, | Pass/Fail Pass/Fail |
| 2 | Institutional Capacity (Company /key personnel/Individual Consultant): (Max-28) - Experience of similar nature of work in following areas completed in the last Ten (10) years (reference copy of the report of similar nature of work. (@2.5/project, Max-10) - Policy Planning & Coordination - Capacity Strengthening - Experience of similar nature of work in following areas completed in the last Ten (10) years (reference copy of the report of similar nature of work. (@2.5/project, Max-10) - Service Delivery Support - Strengthening Supply Chain and Logistics - Monitoring and Evaluation - Communication, Community Engagement, and SBC - Experience in health and nutrition programme with special focus to strengthening health system in Madhesh Province (2 points per project, Max-4) - Working experience with different Agencies (United Nation, Government etc.) (1 point / agency; Max- 4 points) Key personnel: relevant experience and qualifications of the proposed team for the assignment shall be as per section 12 of this ToR (Max- 17) - Team leader (Max: 5 point) @1 point for master's degree in relevant field as mentioned in section-12, additional 1 point for Ph.D @2 points for minimum 5 years' experience @1 point for additional years of experience > 5 years’ experience - Supply chain and logistics management expert (Max: 4 point) @ 1 point for master’s degree in relevant field as mentioned in section-12; @ 2 points for minimum 5 years’ experience @ 1 point for Certificates of Supply chain and logistics management - Training Coordinator (Max- 4 points) @1 point for master's degree in relevant field as mentioned in section-12; @2 point for minimum 5 years' experience @1 point for additional years of experience > 5 years’ experience - M&E and SBC Coordinator (Max- 4 points) @1 point for master's degree in relevant field as mentioned in section-12; @2 point for minimum 3 years' experience @1 point for additional years of experience > 3 years’ experience | 10 10 4 4 5 4 4 4 |
| 3 | Proposed methodology and approach: (Max-25) - Quality and suitability of the proposed approach and methodology - Clear understanding over the context on maternal nutrition program including MMS distribution. - Risk assessment - recognition of the risks/peripheral problems and methods to prevent and manage risks/peripheral problems. (6 points) - Implementation Plan, Timelines proposed must be detailed and realistic. (4 point) | 15 6 4 |
| 4. | Service Provider’s accountability towards Sustainable Procurement - Confirmation of membership of the UN Global Compact Nepal Chapter. (Yes/No) - Copies of relevant ISO certification or any other relevant certification related to “Environment Management Framework” or Copies of policy related to “Environment / Waste Management”. (Yes/No) - Copies of existing organizational policies on Gender Equity, Prevention of sexual harassment, Disability inclusion and any other policies discouraging any other forms of discrimination. (Yes/No) - Copies of existing organizational policies on Labor rights. (Yes/No) - Representation of Gender, Marginalized community in beneficial ownership and proposed staff for this assignment. (Yes/No) - Inclusion of recruitment strategy to recruit team members from local communities within the relevant district / province in which they will be assigned to work. (Yes/No) Bidder has to provide supporting documents for specific initiatives that they have undertaken in the above areas. | (5) Bonus Point 0.5 1 1 1 1 0.5 |
| Total Technical |  | 70+5 points Bonus |
| Only proposals that receive a minimum of 49 points will be considered further. The bidders who achieve a score of 70 or higher, inclusive of the bonus score, during the technical evaluation, will be treated as having achieved 100% scores in Technical Evaluation. |  |  |

b. Financial Proposal

The total amount of points allocated for the price component is 30. The maximum number of points will be allotted to the lowest price proposal that is opened and compared among those invited firms/institutions which obtain the threshold points in the evaluation of the technical component. All other price proposals will receive points in inverse proportion to the lowest price, e.g.:

Max. Score for price proposal * Price of lowest priced proposal

Score for price proposal X = --------------------------------------------------------------------------------

Price of proposal X

Instructions for Financial Quote (Proposal) - see Annex D

Please prepare the expected cost, as per the table below, and Annex D of price tables.  Please note that there are certain elements that will be required at costs.

Table 1: Summary of Financial Proposal

| Estimated financial quote (proposal) for institutional consultancy to support the implementation of MMS program in Madhesh Province |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| SN | Description | Amount of Renumeration Costs | Amount of Other Expenses Costs | Total Cost (NPR) | Remarks |
|  |  | [ Ref: Total Fin 2 (B) ] | [ Ref: Fin 3 (B) ] |  |  |
| D-1 | Deliverable-1 |  |  |  |  |
| D-2 | Deliverable-2 |  |  |  |  |
| D-3 | Deliverable-3 |  |  |  |  |
| D-4 | Deliverable-4 |  |  |  |  |
| D-5 | Deliverable-5 |  |  |  |  |
| D-6 | Deliverable-6 |  |  |  |  |
| D-7 | Deliverable-7 |  |  |  |  |
| D-8 | Deliverable-8 |  |  |  |  |
|  |  |  | Sub-Total |  |  |
|  |  |  | VAT |  |  |
|  |  |  | Total |  |  |

Table 2: Budget Breakdown of Financial Proposal:

# See Annex D

# Annex F

Annex F.1

Table 1: Participants of Advocacy, planning and coordination meeting at federal government

| Level | Training type | Participants | Expected number of participants | Facilitator |
| --- | --- | --- | --- | --- |
| Federal level | MTOT | - Honable Member, Health and Social Service, National Planning Commission - Joint Secretary, National Planning Commission - Director, Health and Social Service, National Planning Commission - Secretary, Ministry of Health and Population - Director General, DoHS - Director General, Department of Drug Administration (DDA) - Director, Health Coordination Division - Director, Policy Planning & Monitoring Division, MoHP - Director, Standardization and Regulation Division, MoHP - Director, Population Management Division, MoHP - Director, Family Welfare Division, DoHS - Director, Management Division - Director, Curative Service Division, DoHS - Director, Epideomology and Disease Control Division, DoHS - Director, Nursing and Social Security Division, DoHS - Director, Administration Division - Director, National Health Training Center - Director, National Health Information Education, Communication Center - Chief, Supply Section, Management Division - Chief, Nutrition Section - Chief, Provincial and local government coordination section, Ministry of Health and Population. - Chief, Integrated Health Information Management Section, Management Division. - Chief, Hospital Service monitoring and strengthening Section, DoHS - Chief, Child Health and Immunization Section, DoHS - Chief, Maternal and Newborn Health Section, DoHS - Chief, Family Planning and Reproductive Health Section, DoHS - Chief, Nursing Capacity Development Section, DoHS - Chief, Genetic and Gender based violence (GBV) , DoHS - Management Section, DoHS - Chief, Social Health Safety Section, DoHS - Chief, Administration Section, DoHS - Chief, Financial Administration Section, DoHS - Chief, Logistic Management Section, DoHS - Chief, Environment Management and Health Waste Management Section - Chief, Basic and Emergency Health Service Management Section, DoHS - Chief, ENT and Oral Health Section. - Chief, Laprosy Control and Disability Management Section - Chief, NTD and Vector Borne Disease control Section, DoHS - Chief, Zoonotic and Infectious Disease Control Section, DoHS - Chief, Disease Monitoring and Research Section, DoHS - Chief, NCD and Mental Health Section, DoHS - Chief, National Health Research Council. - Director, Maternity Hospital, Thapathali - Director, US State Department, US Embassy, Nepal. - Health and Nutrition Specialist, US State Department, US Embassy. - Other partners ( FHI 360, HKI, ECF etc)- 10 in Nos. | 55 | Family Welfare Division |

Annex F.2

Table 2: Participants of Advocacy, planning and coordination meeting at provincial government

| Level | Training type | Participants | Expected number of participants | Facilitator |
| --- | --- | --- | --- | --- |
| Provincial | MTOT | - Minister, Secretary, Sr. Public Health Officer of Ministry of Health and Population [2] - Secretary of Ministry of Finance [1] - Vice Chair, Member (Nutrition focal), MSNP Focal Officer and MSNP Provincial coordinator from Provincial Policy and Planning Commission [4] - Director, Nutrition focal point, Sr. Nursing Administrator, MNH focal point and HMIS/data focal point from Health Directorate/MoHP [5] - Director and Officers from Provincial Health Logistics Management Center [2] - Chief, Centra Medical Store, Pathlaiaya [1] - Secretary of Ministry of Education and Culture Ministry, and Director of Education Development Directorate [2] (Note: School Nurse is through EDD in Madhesh Province). - Director and training officers from Provincial Health Training Center [4] - Director, Provincial Public Health Laboratory [2] - Medical Superintendent and Specialist doctor in Maternal Health eight Federal/ Provincial Hospitals [16] - Nutrition Rehabilitation Center Managers [3] - Development partners (WFP, WHH, WorldVision, SavetheChildren, etc) [10] - Media [4] | 56 | Family Welfare Division |

Annex F.3

Table 3: Participants of Advocacy, planning and coordination meeting at 136 local government

| S.N. | Office holder | Position on the committee | Numbers | Total |
| --- | --- | --- | --- | --- |
| 1 | Mayor, Municipality | Chair | 1 | 136 |
| 2 | Deputy Mayor, Municipality | Deputy Chair | 1 | 136 |
| 3 | All ward chairperson of the Municipality | Members | 10 | 1360 |
| 4 | Women member of municipality designated by Chair | Member | 1 | 136 |
| 5 | Dalit member of municipality designed by Chair | Member | 1 | 136 |
| 6 | Chief of Health Section, Municipality | Member | 1 | 136 |
| 7 | Chief of Agriculture and Livestock Development Section, Municipality | Member | 1 | 136 |
| 8 | Chief of Social Sector Section, Municipality | Member | 1 | 136 |
| 9 | Chief/ Focal Officer of Drinking Water, Municipality | Member | 1 | 136 |
| 10 | Chief/ Focal Officer, Hygiene and Sanitation Programme, Municipality | Member | 1 | 136 |
| 11 | Chief of Women, Children and Senior Citizen Section, Municipality | Member | 1 | 136 |
| 12 | Chief of Education Section, Municipality | Member | 1 | 136 |
| 13 | Chief of Planning Section, Municipality | Member | 1 | 136 |
| 14 | Representative, Nepal Chamber and Commerce, Municipality | Member | 1 | 136 |
| 15 | President or a designated representative from the Federation of non-government organization, Chandrapur Municipality | Member | 1 | 136 |
| 16 | Chief Administrative Officer, Municipality | Member-Secretary | 1 | 136 |
| 17 | MSNP Facilitator | Invited member | 1 | 136 |
| 18 | Food Research Office, Food Technology and Quality Control Office (RFTQC) | Invited member | 1 | 136 |
| 19 | Representative of mother’s group | Invited member | 1 | 136 |
| 20 | Small Farmer Group | Invited member | 1 | 136 |
| 21 | Representative from Institution | Invited member | 1 | 136 |
| 22 | UNICEF Nepal | Invited member | 1 | 136 |
|  | Total members |  | 31 | 4,309 |

Annex F.4

Table 4: Cascade training type and expected participants:

| Level | Training type | Participants | Expected number of participants | Facilitator |
| --- | --- | --- | --- | --- |
| Federal level | MTOT | - Public Health Officers from National Health Training Center and Nutrition Section of Family Welfare Division | 30 | Family Welfare Division |
| Provincial Level | TOT | - Director and Nutrition Focal Point, Health Directorate (1) - Chief and Training officer of Provincial Health Training Center (6) - Chief of Health Office and Nutrition Focal Points/Public Health Officers, 8 Health Office at districts (16) - Nutrition Officers from different agencies working in Nutrition (5) - Selected Public Health Officers/trainers who will be mobilized during TOT (30) | 60 | FWD, UNICEF |
|  | Stakeholder Orientation | - Orientation at the provincial level to all stakeholders: MoHP, Health Directorate, Provincial Health Training Center, (3) - Provincial Health Logistics Management Center, (4) - Provincial Health Laboratory, (1) - Doctors Provincial Hospitals (2 participants) and Federal hospitals (Narayani and Gajendra Narayan Singh Hospital) (3) - MNSP stakeholders, Media, Academia (10) | 25 | FWD and UNICEF |
| District Level | TOT | - Chief and Nutrition Focal Point of Health section of all 136 Municipalities in eight districts (8 batch) and Nutrition officers from different NGOs | 272 | Trainers from MTOT |
| Palika level | Training | - Nutrition focal points/Health Workers, MNH focal point from all 136 Municipalities | 408 | Trainers form TOT |
|  | Orientation | - Nutrition and Food Security Steering Committee members, - NGO partners working in Health and Nutrition at Municipality level. | 31 | Chief and Nutrition Focal Point of Health section |
| Health Facility | Orientation | - Orientation to all Health Workers in Health facility (33 PHC, 748 Health Post, 40 Urban Health Clinic, 242 Basic Health Center), and key influencers for community | 1688 | Chief and Nutrition Focal Point of Health section |
|  | Training | - Training to all FCHVs (7645) | 7645 | Nutrition Focal Point of Health section |
| Community | Mothers Group | - Orientation to mothers group by FCHV (Batch of 40 mothers; Total 3,787 Batches) | 151,461 | Nutrition focal point of Health Facility |
|  | Community Awareness | - Use of appropriate communication models (radio, miking, SMS messaging) | 139 | Miking |

Annex F.5

Table 5: Maternal and Newborn Health Technical Working Committee/ Nutrition Technical Committee meeting to update National Medical Standard for inclusion of MMS in large scale program context.

| Level | Participants | Expected number of participants | Facilitator |
| --- | --- | --- | --- |
| Federal level | - Director, Family Welfare Division, DoHS - Director, Management Division - Director, Curative Service Division, DoHS - Director, Epideomology and Disease Control Division, DoHS - Director, Nursing and Social Security Division, DoHS - Director, Administration Division - Director, National Health Training Center - Director, National Health Information Education, Communication Center - Chief, Supply Section, Management Division - Chief, Nutrition Section - Chief, Integrated Health Information Management Section, Management Division. - Chief, Maternal and Newborn Health Section, DoHS - Chief, Nursing Capacity Development Section, DoHS - Chief, Logistic Management Section, DoHS - Health and Nutrition Partner Organisation ( Nos 5) - Representative from NESOG - Representative from NEPAS - Representative from Nursing Council | 18 | Family Welfare Division |

Annex F.6

Table 6: Supply readiness and ANC/PNC protocol meeting at province level for MMS distribution.

| Level | Training type | Participants | Expected number of participants | Facilitator |
| --- | --- | --- | --- | --- |
| Provincial Level | TOT | Director, Provincial Health Service Directorate (1) Nutrition Focal Point, Health Directorate (1) Chief of District Health/ Public Health Office (8) Nursing Officers/ MNH focal point, Public Health Office (8) Chief, Provincial Medical Store, Madhesh Province (1) MNH focal Point, Provincial Health Service Directorate. (1) MNH focal Point/ Nursing Officer, Ministry of Health, Madhesh Province (1) Representative from relevant partners (5) | 26 | FWD, UNICEF |

Annex F.7

Table 7: Mobilization of FCHVs for referral services to pregnant and lactating women at ANC/PNC services

| Level | Service delivery type | Participants | Expected number of participants | Facilitator |
| --- | --- | --- | --- | --- |
| Local Government | House to house visit (Referral Service) | Female Community Health Volunteers (7645) – 1 time | 7645 | FWD, UNICEF |

Annex F.8

Table 8: Quantification of MMS at Federal Government

| Level | Action | Participants | Expected number of participants | Facilitator |
| --- | --- | --- | --- | --- |
| Federal | Quantification of MMS and development of distribution plan | Logistic Expert | 1 | FWD, UNICEF |

Annex F. 9

Table 9: Forecasting and supply planning meeting at provincial level.

| Level | Meeting type | Participants | Expected number of participants | Facilitator |
| --- | --- | --- | --- | --- |
| Province | Forecasting and supply planning meeting at Madhesh Province | Director, Provincial Health Service Directorate (1) Nutrition Focal Point, Health Directorate (1) Chief of District Health/ Public Health Office (8) Chief, Provincial Medical Store, Madhesh Province (1) Programme Officer – FHI 360 Chief Supply Section, Management Division (1) Logistic Officer, Management Division (1) Procurement Officer, Management Division (1) | 14 | FWD, UNICEF |

Annex F.10

Table 10: One day logistic management training to logistic staff at local government

| Level | Training type | Participants | Expected number of participants | Facilitator |
| --- | --- | --- | --- | --- |
| Local government | Logistic training | 136 stores in charge from 136 Local Government (7 Batch of training with 20 participants in each batch) | 136 | District Health/ Public Health Office |

Annex F.11

Table 11: One day M&E meeting on MMS monitoring at federal level.

| Level | Meeting | Participants | Expected number of participants | Facilitator |
| --- | --- | --- | --- | --- |
| Federal level | M&E meeting on MMS at Family Welfare Division | - Director, Family Welfare Division, DoHS - Director, Management Division - Chief, Supply Section, Management Division - Chief, Nutrition Section - Chief, Integrated Health Information Management Section, Management Division. - Health and Nutrition Partner Organization (Nos 5) | 10 | Management Division |

Annex F.12

Table 12: Technical Support Visits (TSVs) from officials from provincial government

| Level | Supervision/ Monitoring type | Participants | Expected number of participants | Facilitator |
| --- | --- | --- | --- | --- |
| Province | Technical Support Visits | Director, Provincial Health Service Directorate (1) Nutrition Focal Point, Health Directorate (1) Chief of District Health/ Public Health Office (8) Chief, Provincial Medical Store, Madhesh Province (1) Programme Officer – FHI 360 Chief Supply Section, Management Division (1) Logistic Officer, Management Division (1) Procurement Officer, Management Division (1) | 14 | FWD, UNICEF |

Annex F.13

Table 13: Technical Support Visits (TSVs) from officials from local government

| Level | Supervision/ Monitoring type | Participants | Expected number of participants | Facilitator |
| --- | --- | --- | --- | --- |
| Local Government | Technical Support Visits | Chief, Health Section, Local Government (136) | 1063 health facilities | Health Section, Local Government |

Annex F.14

Table 14: SBCC and Training Material design development

| Level | Action | Participants | Expected number of participants | Facilitator |
| --- | --- | --- | --- | --- |
| Federal | SBCC and training material design | SBCC and Training material development expert | 1 | Nutrition Section/ Family Welfare Division |

Annex F.15

Table 15: Adaptation of National Message on Maternal Nutrition in local language of Madhesh Province

| Level | Action | Participants | Expected number of participants | Facilitator |
| --- | --- | --- | --- | --- |
| Province | SBCC and training material design in local language | SBCC and Training material development expert | 1 | Nutrition Section/ Family Welfare Division |

Annex F.16

Table 16: Interpersonal Communication Training (IPC) for Health Workers, ANMs and FCHVs

| Level | Type of training | Participants | Expected number of participants | Facilitator |
| --- | --- | --- | --- | --- |
| Local Government | Internal personal communication training | Health Workers and ANMs from 33 PHC, 748 Health Post, 40 Urban Health Clinic, 242 Basic Health Center | 1063 | Local Government |
|  | Internal personal communication training | Female Community Health Volunteers | 7645 | Local Government |

Annex F.17

Table 17: Knowledge generation and management at federal level.

| Level | Action | Participants | Expected number of participants | Facilitator |
| --- | --- | --- | --- | --- |
| Federal | Development of one technical brief, one report and 8 case studies. | Knowledge generation and management Expert | 1 | Partner organization |
|  | Workshop for sharing best practices in maternal nutrition and MMS distribution. | Government officers from Federal level | 30 | Nutrition Section, Family Welfare Division |

Annex F.18

Table 18: Knowledge generation and management at provincial government.

| Level | Action | Participants | Expected number of participants | Facilitator |
| --- | --- | --- | --- | --- |
| Provincial | Development of at least 8 case studies from 8 districts of Madhesh Province. | Knowledge generation and management Expert | 1 | Partner organization |

Annex F.19

Table 19: Knowledge generation and management at 136 local government.

| Level | Action | Participants | Expected number of participants | Facilitator |
| --- | --- | --- | --- | --- |
| Local | Development of 139 case stories from 139 local government. | Knowledge generation and management Expert | 1 | Partner organization |

# Annex G:

# Deliverables details

Deliverables

- An inception reports inclusive of detail work plan and advocacy, policy, planning and coordination meetings at federal, Madhesh Province and 136 local government of Madhesh Province (D1)

Deliverable details:

- An inception report including detail implementation plan.

- National & provincial maternal nutrition guideline focussing on MMS distribution.

- One minute of advocacy, planning and coordination meeting at federal level.

- One minute of advocacy planning and coordination meeting at Madhesh Province.

- 136 minutes of advocacy, planning and coordination meeting in all local government of Madhesh Province.

- 136 local government’s work plans inclusive of MMS distribution

Note: Inclusion of MMS in 136 local government’s work plan is subject to fiscal year cycle for local level planning process. If these could not materialise at the beginning of the project cycle, it needs to present at the end of the project to ensure sustainability of the project using government resources.

- Report on Health Sector’s human resources capacity strengthening in Madhesh Province to deliver maternal nutrition programme inclusive of MMS distribution (D2)

Deliverable details:

- A facilitator guideline, a health worker’s guideline and a training package on maternal nutrition inclusive of MMS distribution.

- List of 30 national level trainers (Government, federal level) on maternal nutrition inclusive of MMS distribution at federal level.

- List of 60 provincial level trainers (Government, Provincial level) on maternal nutrition inclusive of MMS distribution at Madhesh Province.

- One report on stakeholder’s orientation at Madhesh Province.

- List of 272 trained personnel (Government, District level) on maternal nutrition inclusive of MMS distribution in 8 districts of Madhesh Province.

- List of 408 trained personnel (Government, Local Government) on maternal nutrition inclusive of MMS distribution at 136 local government of Madhesh Province.

- Collection of 136 reports of orientation on maternal nutrition including MMS distribution to members of municipality level nutrition and food security steering committee and other representatives from NGO/CBOs partners working in municipality.

- List of 1688 oriented personnel (Government, Health facility level) on maternal nutrition inclusive of MMS distribution at Health facility level. - List of 7645 trained Female Community Health Volunteers (FCHVs) on maternal nutrition inclusive of MMS distribution at community level. - List of 151,461 mothers oriented on maternal nutrition inclusive of MMS distribution at community level. - Report on the 136-community awareness campaign in community level to keep mothers aware about the MMS distribution.

Note: All capacity building activities focus on the government staff at federal, provincial and local government, however, other personnel from NGOs/CBOs can participate in the capacity building efforts on the cost of concern NGOs/CBOs without additional financial burden to the project. In addition, capacity building effort will follow cascade method – trainers in federal government will provide training to provincial government; trainers in provincial government will provide training to local government, and trainers at local government will provide training to health facility and community level training. Those participating in the community level training will further organize community level activities like mother’s group meetings and referral services and community level awareness campaigns.

- Report on strengthening service delivery system in Madhesh Province (D3)

Deliverable details:

- Seconded supplementary standard on maternal nutrition inclusive of MMS distribution for Nepal for revising updating National Medical Standard for maternal and newborn care, Volume III, Government of Nepal, MoHP, DoHS, FWD, 2022.

- At least two minutes of joint meetings between the members of maternal and newborn health technical working committee and nutrition technical committee at federal level for revising/updating National Medical Standard for inclusion of MMS in large scale programme context.

- A set of training package, job aids and supportive supervision tools (checklist) focussing on capacity building of health workers, health supervisors and health programme managers on maternal nutrition inclusive of MMS distribution.

- Revised/updated provincial antenatal care to postnatal care (ANC-PNC) continuum of care guideline inclusive of MMS distribution in Madhesh Province.

- At least one minute of supply readiness and ANC/PNC protocol update meeting of Provincial Health Service Directorate at Madhesh Province.

- A report of 151,461 pregnant women screened for anaemia in 18 public hospitals and 32 primary health care canters (PHCC) in Madhesh Province

- A report of 7645 female community health volunteers (FCHVs) mobilisation for house to house visit to refer 151,461 mothers’ pregnant women to nearest health facilities to receive nutrition education, counselling and multiple micronutrient supplements (MMS) tablet distribution services.

Note: Maternal anaemia screening services will be supported directly through provincial health service directorate. The institution role here will be linking pregnant women to receive these services at 18 public hospitals and 32 primary health care centers (PHCC).  The institution will not be liable to direct invest for this activity, however, will remain responsible to link pregnant women with these services.

- Report on supply chain and logistic system strengthening to forecast, quantify and deliver MMS supplements to pregnant and lactating women in Madhesh Province (D4)

Deliverable details:

- A report on capacity building at federal level for annual quantification (forecasting and supply planning) on Maternal Micronutrient Supplements (MMS) tablet.

- A supply chain management report of maternal micronutrient supplements (MMS) from Madhesh Province describing the status of authorized stock levels (ASL) and emergency order points (EOP) of MMS tablet throughout the year at the federal, provincial and local health facility level and corrective action taken from the vendor’s side to prevent stock out of MMS at Health facilities.

- At least one minute of supply chain management of maternal micronutrient supplement (MMS) from Madhesh Province.

- A list of 136 trained stores incharges from local government to store, handle and distribution of multiple micronutrient supplements (MMS) tablet at local government and health facilities.

- Report on Information System Strengthening to record, report, analysing the data and digital reflection on the progress made on MMS coverage and adherence using dashboard including technical support visits at all three tiers of government (Federal, Madhesh Province and 136 Local Government) (D5)

Deliverable details:

- A seconded supplementary indicator profile on coverage and adherence on maternal micronutrient supplementation (MMS) to be included in forthcoming revised Health Management Information System (HMIS) Indicator booklet of Department of Health Services (DoHS), Ministry of Health and Population (MoHP) Nepal.

- A minute of discussion and consensus building among the concern Divisions (Family Welfare Division and Management Division) and Sections (Nutrition Section, Supply Section, Integrated Health Information Management Section) focusing on following two issues:

  - To include indicators related to maternal nutrition and MMS distribution in upcoming revision of HMIS indicator booklet taking reference of seconded supplementary indicator profile on coverage and adherence on MMS.

  - To manage MMS related information in Madhesh Province through regular DHiS/IHMIS using existing information management system of maternal iron folic acid supplementation.

- Quarterly and annual reports on coverage and adherence on maternal micronutrient supplementation (MMS) analyzing the records of MMS supplementation to pregnant women at Madhesh province using existing DHiS2/ Integrated Health Information Management System (IHIMS).

- One compiled report from institution on technical support visit (TSV) provided by the Chief of Health Section of 136 Local Government during monthly review meeting of 1063 health facilities of Madhesh Province to ensure quality services for pregnant & lactating women on maternal nutrition education & counselling and MMS distribution from ANC/PNC platforms.

Note: During the Technical Support Visit, the Chief of Health Section is expected to interact with the Health Facility Incharges and Auxillary Nurse Midwives (ANMs) on the status of MMS coverage and adherence based on the local evidence generated from DHiS/IHIMS and discuss on positive and negative factors that affecting the performance. If any low coverage and adherence observed in maternal MMS coverage and adherence, Chief of Health Sections are expected to take corrective action base on the local situation.

- Report on communication, community engagement and SBC to empower pregnant and lactating women for receiving maternal nutrition services and adhere with the MMS compliance (D6)

Deliverables details:

- Print file of MMS distribution guidance note – Statistical Information Collection support material (A4 size, 4 pages),

- Print file of MMS reminder calendar (A4 size),

- Print file of MMS brochure (A4 size) for mothers

- Print file of MMS facilitator guideline for Health Workers (A3 Size, 8 pages)

- Print file of MMS flip chart for FCHVs (A4 size, 34 pages)

- Print file of MMS registers (A4 size) for ANC/PNC clinics.

- Print file of MMS reporting forms (A4 Size) for ANC/ PNC clinics and health facilities

- Print file of Maternal Nutrition Card (A4 Size) for pregnant and lactating mothers

- Print file of MMS Reference Manual (A4 Size)

- Public service announce (PSA) material (One radio zingle and one maternal MMS promotional digital message) on Nepali language focusing on pregnant and lactating women.

- Public service announcement (PSA) materials (4 radio zingle and 4 maternal MMS promotional digital message) on Maithili, Awadhi, Bhojpuri and Bajika language focusing on pregnant and lactating women living in Madhesh Province.

- A list of trained health facility incharges and auxillary midwives (ANMs) from 1063 health facilities (Health Workers and ANMs from 33 PHC, 748 Health Post, 40 Urgan Health Clinics and 242 Basic Health Centers) on interpersonal counselling to pregnant and lactating women on maternal nutrition practices and adherence with the MMS tablet (225 tables) during pregnancy and postpartum period.

- A list of trained Female Community Health Volunteers (FCHVs) on interpersonal communication with pregnant women on the importance of maternal nutrition and MMS tablet during the pregnancy and postpartum period.

Note: The institution will work closely with the Nutrition Section of Family Welfare Division to adopt already existing training material and SBC materials to adopt it in local context of Madhesh Province and also, ensuring the brand visibility of US Department of State, UNICEF, Government of Nepal and other partners who contributed in research and further scale up of MMS programme in Nepal. However, the brand visibility is subject to approval of the logo from the concerned institutions where UNICEF will coordinate to receive approval. The services to print all these materials will be provided through UNICEF Supply Unit, Operation Section upon the vendor submits the print file of all these materials to UNICEF in coordination with the Nutrition Section of Family Welfare Division, Ministry of Health and Population (MoHP) Nepal. The PSA will be aired directly through UNICEF Long Term Agreement (LTA) media partners in consultation with the National Health Education, Information and Communication Center (NHEICC).

- Report on knowledge generation and management inclusive of technical briefs, case studies, best practice sharing workshop (D7)

Deliverables details:

- One technical brief, one report and 8 long case story on maternal multiple micronutrient supplements (MMS) tablet distribution to pregnant and lactating women in Nepal under US Department of State and UNICEF joint support to Government of Nepal.

- One technical brief, one report and 8 short case story on maternal multiple micronutrient supplements (MMS) tablet distribution to pregnant and lactating women in Madhesh Province under US Department of State and UNICEF joint support to Government of Nepal

- At least one short case story from one local government on MMS distribution in the local government (total 139 case story on MMS distribution).

- A learning workshop at national level to share the best practices in maternal nutrition and MMS distribution in Madhesh Province.

Note: In the learning workshop, technical brief, brief, selected 8 story from the Madhesh Province, photo story will be shared to enhance the knowledge of key listeners (policy makers, planners, journalist, influencers etc) on the importance of maternal nutrition and MMS distribution for the health and nutrition well being of pregnant and lactating women. It is expected that this knowledge sharing will contribute in further scaling up of maternal nutrition and MMS programme in other provinces of Nepal. Also, it will contribute in the donor’s visibility.

- Submission of final report on maternal nutrition programme inclusive of MMS distribution in Madhesh Province (D8)

Deliverables details:

- A monthly virtual update with short summary- not more than five-page report on progress and challenges to implement maternal nutrition inclusive of MMS distribution in Madhesh Province.

- Format of comprehensive report on implementation of maternal nutrition inclusive of MMS distribution programme in Madhesh Province.

- Draft comprehensive report on implementation of maternal nutrition inclusive of MMS distribution programme in Madhesh Province (80 page, Maximum)

- Final comprehensive report on implementation of maternal nutrition inclusive of MMS distribution programme in Madhesh Province (80 page, Maximum)

- High quality pictures of maternal nutrition inclusive of MMS distribution in Madhesh Province.

- Powerpoint presentation for dissemination of final comprehensive report on implementation of maternal nutrition inclusive of MMS distribution in Madhesh Province.

- Report on dissemination meeting on maternal nutrition inclusive of MMS distribution in Madhesh Province.

UNICEF will  facilitate  for coordination with NGO for the list of Nutrition Officer

The implementing agency will support in interpersonal communication training to FCHVs for one day and local health institution will mobilize these FCHVs for encouraging pregnancy women to complete 8 ANC/ 4 PNC package through visiting nearest ANC/PNC clinic.

Note: Please refer to annex 2 for detail description of each deliverables that need to include in the report.

Relevant task of each activity as mentioned in section-5 of this ToR has to be completed

Payment percentage will be updated as per financial proposal of selected Bidder

of Lead Partner

During kick- meeting after contract signing or execution of contract, if Contract Manager is not satisfied with any key personnel, S/he may request to replace that key-personal in consultation with Supply unit.

Team Leader has to be full time staff of Lead Partner